## UAT Rule Engine
S.No | Task Name | Assigned To | Priority | Efforts(Days) | Dependency | Status | Completed date | Remarks
1 | Java Installation | Mohan | High | 0.5 |  | Completed | 2021-11-10
2 | App server Installation | Mohan | High | 0.5 |  | Completed | 2021-11-10
3 | Database Configuration for RuleEngine | Mohan | High | 1 | Database sever details and credentials | Completed | 2022-01-17
4 | RuleEngine App Deployment | Mohan | High | 1 |  | Completed | 2022-01-17
5 | RuleEngine user Configuration | Mohan | High | 2 | User details and respective roles need to be provided | Completed | 2022-01-17
6 | Implement HTTPS | Mohan | High | 2 | Certificate details to be provided by SIB | Open
7 | LDAP Integration | Mohan | High | <TBD> | LDAP details to be provided by SIB | Open
8 | SIB Rules Configuration | Mohan | High | 5 | Browser compatiblity for uploading the master list.Requested to install chrome browser in site | In Progress |  | Out of four rules, two rules fully configured and remaing two is in progress
9 | Rule Execution API Testing | Mohan | High | 5 |  | In Progress |  | For two rules testing done
10 | Audit Logs Testing for Rule, Variable and Users | Mohan | High | 3 |  | Yet To Start
11 | Rule Execution API Integration and Testing | Mohan , CTI team | High | 5 | Authorised IP list need to be provided | Open