## TEAM_COMPOSITION
TEAM COMPOSITION AND TASK ASSIGNMENTS
No
1 | JOB TITLE | Senior systems Engineer
| FULL NAME | Sinan Hassan P S
| LANGUAGES | ENGLISH good in speaking, reading, and writing, ARABIC fair in speaking
| DETAILED TASKS ASSIGNED | UCCX installation and configurations
| WORK UNDERTAKEN THAT ILLUSTRATES CAPABILITY TO HANDLE THE TASKS ASSIGNED | 1.Name of Project : Dubai Tourism and Economy Contact Centre Project Year : 2022 Location : Dubai, UAE Main Project Features : IVR solution on UCCX platform integrated with DTCM hosts and applications providing enhanced customer and user experience. Solution include Eleveo WFO solution, 2 Ring Wallboard solution, CRM integration, outbound Campaign manager integration. Position Held : Project Engineer Activities performed : Solution design, Implementation, Integration, multi vendor and internal team coordination. | Name of Project : Land force UAE (Ministry of Defence) Contact centre. Year : 2022 Location : Abudhabi, UAE Main Project Features : IVR solution with customer hosts and applications . Solution include quality management solution, Wallboard solution and CRM integration. Position Held : Project Engineer Activities performed : Solution design, Implementation and Integration, | Name of Project : STC Bahrain contact Centre Upgrade and Migration. Year : 2023 Location : Manama, Bahrain Main Project Features : IVR solution on Cisco UCCE platform integrating with cloud solutions, customer hosts and applications . Solution include verint WFM solution, 2 Ring Wallboard solution, CRM integration, Outbound IVR solution, Reporting Modules, Position Held : Project Engineer Activities performed : Solution Upgrade from older version to new version, Data migration and operation switch over.
2 | JOB TITLE | CISCO IVR DEVELOPER
| FULL NAME | RANGITHA.S
| LANGUAGES | ENGLISH good in speaking, reading, and writing,
| DETAILED TASKS ASSIGNED | IVR Callflow development, Deployment and support
| WORK UNDERTAKEN THAT ILLUSTRATES CAPABILITY TO HANDLE THE TASKS ASSIGNED | Name of Project: Digital14 Year: 2022 Location: Dubai, UAE Main Project Features: Developed IVR for Main Flow, CallBack & Survey Application, Agent admin integration with agent desktop, testing outbound campaign with manual data, integrating survey UI with survey application and checking on the rating reports, Checking on CUIC Report, worked on-screen pop and browser pop, CRM API intergration. Position Held: IVR Developer Activities performed: Solution design, Integration, Implementation, Development, and Testing. | Name of Project: Family Development Foundation. Year: 2022 Location: Abudhabi, UAE Main Project Features : IVR solution with customer applications. Changes required in the existing flow were worked on in the script and supported whenever normal patches of changes were required. Position Held: IVR Developer Activities performed: Solution design, Implementation and Integration, Development, Testing,
3 | JOB TITLE | Technical Manager
| FULL NAME | Pragadees J
| LANGUAGES | ENGLISH good in speaking, reading, and writing
| DETAILED TASKS ASSIGNED | API Development for Manage Engine Interaction, Survey Reports
| WORK UNDERTAKEN THAT ILLUSTRATES CAPABILITY TO HANDLE THE TASKS ASSIGNED | Name of Project: Digital14 Year: 2022 Location: Dubai, UAE Main Project Features: API development for Survey IVR and Other middleware services Position Held: API developer Activities performed: Solution design, Integration, Implementation, Development, and Testing. | Name of Project: Family Development Foundation. Year: 2022 Location: Abudhabi, UAE Main Project Features: API development for Survey IVR and Other middleware services Position Held: API developer Activities performed: Solution design, Integration, Implementation, Development, and Testing. | Name of Project: ISON Year: 2022 Location: Dubai, UAE, [Multiple Location] Main Project Features: API development for ISON reports Position Held: Solution Architect and API Developer, Activities performed: Solution design, Integration, Implementation, Development, and Testing. Deployment and maintaining the production services in cloud environment(AWS)
4 | JOB TITLE | System Engineer
| FULL NAME | Hussen S
| LANGUAGES | ENGLISH good in speaking, reading, and writing,
| DETAILED TASKS ASSIGNED | UCCX installation and configurations and support
| WORK UNDERTAKEN THAT ILLUSTRATES CAPABILITY TO HANDLE THE TASKS ASSIGNED | Name of Project: <> Year: Location: Main Project Features: Support Role Position Held: UC (Unified Communication and Network Support): Activities performed: Troubleshoot inbound & outbound calling issues, CUCM, CUC , Troubleshoot Jabber login issues, IP phone registration issues, CUBE licence issues, Upgraded CUCM clusters for multiple regions as part of refresh upgrades, perform CUCM upgrade and reboot CUCM nodes in case of any issues, shut down CUCM nodes in case of any power activity and Perform IOS upgradation on switches, router
5 | JOB TITLE | Senior Director(Product & Services)Delivery
| FULL NAME | Indumathi Pandiyan
| LANGUAGES | ENGLISH good in speaking, reading, and writing,
| DETAILED TASKS ASSIGNED | Project Management and Technical Management
| WORK UNDERTAKEN THAT ILLUSTRATES CAPABILITY TO HANDLE THE TASKS ASSIGNED | Name of Project: Digital14 Year: 2022 Location: Dubai, UAE Main Project Features: Developed IVR for Main Flow, CallBack & Survey Application, Agent admin integration with agent desktop, testing outbound campaign with manual data, integrating survey UI with survey application and checking on the rating reports, Checking on CUIC Report, worked on-screen pop and browser pop, CRM API intergration. Position Held: Project Management Activities performed: Oversee all the End to end project activities from defining its requirements to evaluating the finished project and timely project delivery | Name of Project: Central Bank Of Oman Year: 2021 Location: Oman Main Project Features: IVR flow for Service Desk, Dynamic IVR configurations, Survey, Call back solution Position Held: Technical Program Management Activities performed: Technical Design of Dynamic IVR &Oversee all the End to end project activities from defining its requirements to evaluating the finished project and timely project delivery

## SOW_Complaince
COMPLIANCE TO SCOPE OF WORK AND REQUIREMENTS MATRIX
| REFERENCE TO REQUIREMENTS DOCUMENT (PART B) | BIDDER’S RESPONSE
NO. |  | NOTED | COMPLIED | DETAILS OF DEVIATION / ASSUMPTIONS | REFERENCE TO ATTACHMENTS
|  | (Y/N) | (Y/N)
1 | Contact center platform: Cisco UCCX with 15 agent licenses (final quantity will be provided at the later stage) |  | Y
2 | DTMF based IVR call flow development and integrations. |  | Y
3 | Integrating self-service IVR with Manage Engine and Secret double Octopus. The integration would be through API’s. |  | Y
4 | Call Survey module for clients to provide their feedback on the IVR. |  | Y
5 | Call back management module for callers waiting above a threshold time in the queue those need to be called back. |  | Y
6 | Configuration of voice channel on the Cisco UCCX platform. |  | Y
7 | Reporting and analytics powered by Cisco CUIC reporting. |  | Y
8 | Real-time dashboard and wallboard for displaying on the LED screens the contact center KPI’s for voice and non-voice channels as pulled from Manage Engine. |  | Y | ManageEngine to be provide the details in compatible to 2RING
9 | Deployment of Quality monitoring solution for the contact center. |  | Y
10 | Hardware & Software requirements:The bidder to propose optional hardware that is required for the complete solution as well as to highlight the required VM resources in case we decided to hosted on our own hardware servers. |  | Y
11 | Call Back Option:If any caller waiting in the Queue the System will collect the call back request from the caller and present it as a preview campaign to the outbound agents |  | Y
12 | Post Call Survey Application: At the end of every inbound call, if the customer is willing to provide feedback / survey, then the agents would transfer the call to the survey IVR application. The Call survey application will be in English and Arabic with the below features: • The application would announce a max. of 5 questions to callers. • The answers would be either Yes/No or Ratings (1-5) based. • The application would accept DTMF inputs only. • The questions and their corresponding responses will be read from a configuration file. |  | Y
13 | Call Survey, feedback, customer happiness: Inbound Process flow: Caller calls the contact center. • IVR prompts the caller for language selection. • Caller is provided with main menu options based on the language chosen. • Caller navigates various menus from level 1 to level 5 in the IVR. • Upon completing the menu traversal in IVR, caller is prompted in IVR,whether caller is willing to participate in the call survey. • If caller accepts to take part in the survey, the IVR application will log the information in the database. • The survey application will provide list of options to the caller to measure satisfaction level. • Caller will provide input in Survey Application, for example the caller is conveyed to choose the response from scale of 1-5. • This survey responses data will be updated in database for reporting purpose
14 | Manage Engine & Secret Double Octopus (SDO) integration:The Cisco UCCX system will be integrated with Manage Engine and Secret Double Octopus (SDO) to provide the ticket related details for e.g., Existing ticket status, opening a new ticket history etc. and for authenticating the caller. Application links : 1. Components - Secret Double Octopus 2. Zoho ManageEngine ServiceDesk Plus - IT service desk software
15 | Cisco Reporting:• Cisco Unified Intelligence Center (CUIC ) • Cisco Unified Intelligence Center administrative reports
16 | Realtime Wallboard/ Dashboard: Dashboard should support Edge browser, Tablets, mobile phones, and Smart TVs • Key performance indicators (KPIs) should be included in dashboards. The data are stored in the MS SQL server database, providing flexibility to create / build our own KPIs. • In order to meet business needs, we need to go with a wallboard solution suite that can both meet current needs and scale up for future enhancements.
17 | o Call Recording:Recording: Record your interactions. Stores recordings in a single database. The ability to review and play back calls at any time. • Customizable Configurations: Easily create recording rules based on the type, source, and customer of our call data. • Auto Pause and Resume: Protects other parties' sensitive information. • Live Monitoring: Listen to customer interactions and evaluate agent. performance in real-time. • Comprehensive Audits: such as log-ins, log-outs, executed searches, monitored calls, and shared documents.
18 | Quality Management:Quality Management:In order to enable users to monitor and manage customer service agent behaviour.

## Project_plan
NO. | TASKS | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10
1 | Assessment and Analysis of Existing setup
2 | Pre-requisties and Site readiness check
3 | Functional Requirement Gathering and solution delivery
4 | Cisco Gear Delivery
5 | Deployment and configuration of UCCX gear, call recording and Quality Management
6 | IVR call flow design and development, call back and call feedback setup
7 | IVR call flow, call back and call feedback module deployment
8 | IVR callflow integration with ManageEngine and SDO
9 | Realtime Dashboard and wallboard deployment
10 | Testing
11 | Traning and Documentation
12 | UAT & Go Live

## ScheduleFor Resources
NO. | Resources | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10
1 | Sinan
2 | Hussen
3 | Rangitha
4 | Belvin
4 | Pragadees
5 | Vinoth
6 | Indu

## EffortsSpent
Efforts details
Efforts spent Already | In days | Efforts Spent
Requiement clarifications and Document preparation | 3
IVR and middleware service sdevelopment | 36
Cisco support [Spent] | 10
Pending work |  | Pendng work effort
Pending work , double octopus | 10
Cisco Support | 22
End to End testing | 4
Project Management | 5

## EBS_Completed work Till Date
S.No | Task List | Required Efforts (in days) | Assigned To | Planned Start Date | Planned End date | Status | Remarks
Development Tasks
| IVR script Development [Phase 1] | 4 | Rangitha | 2023-11-04 | 04-14-2023 | Done
| IVR script Development [Phase 2] | 8 | Rangitha | 2023-01-05 | 2023-11-05 | Done | In Phase 2 only one API issue Re-open is pending existing and new case is done
| Browser Pop configuration | 1 | Rangitha | 04-18-2023 | 04-19-2023 | Done
| Voicemail through IVR script Development | 2 | Rangitha | 2023-01-05 | 2023-02-05 | Done
| IVR integration with ManageEngine | 2 | Rangitha | 2023-10-05 | 2023-12-05 | Done
| Onsite Deployment IVR development[Phase -1] | 2 | Rangitha | 04-18-2023 | 2023-08-05 | Done
| Emergency Phone integration | 0.5 | Rangitha | 2023-02-05 | 2023-02-05 | Done
| voice Mail integration | 0.5 | Rangitha | 2023-01-05 | 2023-01-05 | Done
| Voice mail through IVR | 2 | Rangitha | 2023-01-05 | 2023-04-05 | Done
| Onsite Deployment [Phase -2] | 4 | Rangitha | 2023-05-12 | 2023-07-28 | In Progress | Phase 2 API integration for Existing case and new case is completed For Re-open case we need to work on API issue
| CallBack development[Phase- 2] | 5 | Rangitha | 2023-07-19 | 2023-07-28 | Done | The Uccx trial version has been expired and renewed again by EBS after that CallBack script was not working as expected. Again deployed the script and tested why the call is not landing to IVR Now the call is landing fine and completed
Support Task
| Trigger Configuration | 0.5 | Rangitha | 04-20-2023 | 04-20-2023 | Done
31 days
Edge Desk | Middleware Services Development | 5 | Hinduja |  |  |  | Done
36 Days

## EBS_Upcoming or pending Work
S.No | Task List | Required Efforts (in days) | Assigned To | Status | Remarks
Development Tasks
Script Development | API Re-open Case IVR script Development [Phase 2] | 1 | Rangitha | In Progress
Script Development | New Requirement Task [Phase 2] script development | 2 | Rangitha | In Progress | Based on the requirement need to estimate
Script Development | Double octopus URL Integration | 2 | Rangitha |  | Based on the requirement need to estimate
| Double octopus API integration | 3 | Vinoth
Script Deployment | Survey Application deployment | 1 | Rangitha
Survey UI Configuration | Survey Application UI configuration | 1 | Rangitha
Support Task
Testing | New Requirement Task [Phase 2] script development Testing | 1 | Rangitha
Testing | Survey Application UI configuration and Testing | 1 | Rangitha
OverAll Testing | If all changed completed end to end testing | 2 | Rangitha
SINAN EFFORT
Development Task | Cisco UCCX( ( coordinate, design, deploy, configure, integrate, testing and documentation)) | 10 days | Sinan | New Development
| Cisco CUCM cluster( 2 nodes Installation and Contact centre related configurations only) | 4 Days | Sinan | New Development
| Voice gateway with PRI\SIP with channels as per call volume requirement | Did not mention |  | New Development | It is required to have dedicated PRI\SIP channels from service provider for contact centre as per expected call volume.
| Eleveo | Did not mention |  | New Development | Requirement to be provided by eleveo (HW spec, efforts)
| 2 Ring(Design, system preparation, Deployment and connector configuration and Integration) | 5 Days |  | New Development
| 2 Ring(Layout configuration) | 2 days per 1 layout |  | New Development | design, configuration, testing and validation

## Resource&Project Plan(Bidder)
SCHEDULE OF RESOURCES
NO. | RESOURCE | WEEK 1 (7Aug-11Aug) | WEEK 2 (14Aug-18Aug) | WEEK 3 (21Aug-25Aug) | WEEK 4 (28Aug-01Sep) | WEEK 5 (4Sep-8Sep) | WEEK 6(11Sep-15Sep) | WEEK 7 (18Sep-22Sep) | Totall Days
1 | SINAN | Cisco CUCM cluster( 2 nodes Installation and Contact centre related configurations only) | Cisco UCCX( ( coordinate, design, deploy, configure, integrate, testing and documentation)) | Cisco UCCX( ( coordinate, design, deploy, configure, integrate, testing and documentation)) | 2 Ring(Design, system preparation, Deployment and connector configuration and Integration) | 2 Ring(Layout configuration) | 1) Voice gateway with PRI\SIP with channels as per call volume requirement 2) Eleveo | 1) Voice gateway with PRI\SIP with channels as per call volume requirement 2) Eleveo Comments: May be based on the requirement to coordinate with other teams for installation process extra one week | 35 Days
2 | RANGITHA | New Requirement Task [Phase 2] script development/Testing | Double octopus URL Integration/Testing | Survey Application deployment/Testing | Survey Application UI configuration /Testing | API Re-open Case IVR script Development [Phase 2] | Complete testing or for any changes required during development need to check in this week |  | 30 Days
3 | HUSSEN
PROJECT PLAN- Rangitha
NO. | TASKS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7
1 | (New Requirement Development/ Phase-2 Development | In the Existing option, we have the following ticket status but for particular Awaiting status alone we need to prompt as In progress status only to the customer not as Awaiting Approval | VIP User Authentication for other departments | In the Non business hour need to have agent transfer call from 5pm to 7pm after that only voicemail and callback will be active still next business hour. | If the agent answered the call before and has been closed the ticket and again the same customer is asking to reopen the case will that call will be transferred to the same agent to reopen | And in the reopen case what is the comment given by the agent in the manage engine resolution also need to prompt out
2 | Double octopus URL Integration/Testing
3 | Survey Application dvelopment and deployment | Develop the Survey application call flow | Survey application configuration in server | Database check rating is been updated or not
4 | Survey Application UI configuration /Testing
5 | API Re-open Case IVR script Development [Phase 2]
6 | Complete testing or for any changes required during development need to check in this week